## Agency SRR v0.4
Risk ID | Date Added | Risk Type | Risk Description | Untreated Impact | Untreated Likelihood | Inherent Risk Score | Current Impact | Current Likelihood | Residual Risk Score | Change in Risk Score due to Action | Key Mitigating Controls-Current and Proposed | Control Confidence Level (NOT IN USE) | Actions | Risk Response | Risk Score Movement | Tolerance Level | Impact Date | Action Owner | Risk Owner | Changes to Risk Explanation | NOTES | Theme
AS-R001a | 2019-01-23 | Programme |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Insufficient |  |  | Static | 15 |  |  | Miriam Craven, James Wallace and Jane Richardson |  | 09/01/20- Discussion held around risk category "Programme" and more detail needed. To be jointly owned by Deputy Directors Linked to ASR034a (based on Agency expectations and clarity on requirements). | 27/04/20 External Relationship/Stakeholder- Retain with different category- Operational Readiness- and risk needs to be rephrased for clarity of expectation on relationship with Programme. REPHRASE
AS-R002a | 2019-01-23 | Operational Delivery |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Reasonable |  |  | Static | 20 |  | AM | Miriam Craven |  | 14/02/20- AM Assigned as new Action Owner | 27/04/20 Operational Readiness- could be linked to AS-R001a above as thematically almost identical in how the Agency manages its key dependencies and stakeholders.
AS-R010a | 2018-03-06 | Communications |  | 3 | 3 | 9 | 3 | 3 | 9 | 0 |  | Insufficient |  |  | Static | 20 |  | KS | Miriam Craven | Based on recent Internal Audit review of communications (March 2019) sufficient mitigations are in place to reduce the risk score from 4x4 to 3x3 | Updated 18/09/19 by Action Owner 26/08/19-update from Hardip Devsi (Accessibility and Inclusive Design Lead)- contracts in place to cover suppor for those who English is not their first language. Merged Risks ASR010, ASR028 & ASR051 Additional text added to risk to expand on impact. | 27/04/20 Inclusive Comms- Reputation- Culture-risk needs to be deep dived and rephrased. Ownership needs to be shared across Agency. REPHRASE
AS-R011a | 2019-01-23 | Governance |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Insufficient |  |  | Static | 15 |  | MG | Miriam Craven |  | 09/01/20- The original risk shared with action owner. | 27/04/20 External Relationships/Stakeholders- Reputational Risk- Culture Risk needs to be rephrased and re-categorised.
AS-R012a | 2019-03-06 | Financial |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Limited |  |  | Static | 15 |  | SG | James Wallace
AS-R014a | 2019-03-06 | Compliance |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Limited |  |  | Static | 10 |  | NM/CK | Miriam Craven |  | 09/01/20- Meeting to be arranged to meet with action owners and split risk (discussed at Risk Review Group #2) | 07/05/20- New risk has been proposed and will be presented to the Risk Review Group in May 20- if accepted this risk will be terminated and removed from the register. 27/04/20 Reputation- Financial- de-escalate for deep dive.
AS-R015a | 2019-01-23 | Policy |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Limited |  |  | Static | 15 |  | MF | James Wallace |  |  | 27/04/20 Finance- Reputation- Cultural- Behaviour Possible rephrasing.
AS-R017a | 2019-01-23 | Policy |  | 2 | 4 | 8 | 2 | 4 | 8 | 0 |  | Reasonable |  |  | Static | 15 |  | CB | Miriam Craven |  | Update from Action Owner 26/08/19 New PM in Westminster 25th July 2019 Merged Risk ASR017 & ASR049 | 27/04/20 External Relationship/Stakeholder, Operational Readiness and Reputation-
AS-R029 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 | 5 | 5 | 25 | 0 |  | Limited |  |  | Static | 20 |  | JC | Janet Richardson |  | 29/01/20- Action to present proposal to split risk in to two 24/01/20- Action Owner now confirmed asJC | 27/04/20 Operational Readiness- Finance- Information Security- Behaviours- but risk needs to be phrased. Look at the word "reative management"- what is the actual risk. REPHRASE
AS-R032a | 2019-01-23 | Resource |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Limited |  |  | Static | 20 |  | NB | James Wallace |  |  | 27/04/2020 Dundee as HQ- Culture- People
AS-R034a | 2019-01-23 | Resource |  | 5 | 5 | 25 | 5 | 5 | 25 | 0 |  | Limited |  |  | Static | 20 |  | JS | James Wallace |  | 14/11/19- Risk now transferred from Programme in full. Risk to be closed on Programme risk register as ownership and control now with Agency. Updated from Action Owner 05/08/19. | 27/04/20 Dundee as HQ- Operational Readiness- People- Workforce Planning- External Relationships- Reputational Risk needs be broken down as multiple threats contained within- links with AS-R001a REPHRASE
AS-R037a | 2019-01-23 | Resource |  | 5 | 4 | 20 | 5 | 4 | 20 | 0 |  | Limited |  |  | Static | 20 |  | NB | James Wallace |  |  | 27/04/20 External Relationships/Stakeholders- Culture- People- Reputation Issue in some areas- especially under COVID-19
AS-R040a | 2019-01-23 | Resource |  | 3 | 2 | 6 | 3 | 2 | 6 | 0 |  | Limited |  | Treat | Static | 20 | 2020-04-30 | SA | James Wallace |  | Risk rephrased. | 27/04/20 Culture, External Relationships/Stakeholders, Financial, Reputational De-escalate
AS-R044 (AG-005a) | 2019-01-30 | Operational Delivery |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Insufficient |  |  | Static | 20 |  | LM | James Wallace |  |  | External Relationships/Stakeholders, Reputation De-escalate
AS-R045 (H&S-R010) | 2019-01-30 | Security |  | 5 | 3 | 15 | 5 | 3 | 15 | 0 |  | Limited |  |  | Static | 15 | 2019-07-05 | GS | James Wallace |  | Linked to Local H&S Risk Register. | 27/04/2020 De-escalate for now.
AS-R047 | 2019-01-30 | Operational Delivery |  |  |  |  | 5 | 4 | 20 | -20 |  | Limited |  |  |  | 20 |  | AM | James Wallace |  | Update 04/09/19- After discussion with Risk Owner it has been decided that this risk needs to be broken down and reflected in a more suitable way. Risk Owner is currently reflected as Action Owner until deep dive has been conducted. Updated 12/08/19- This risk is mirrored from Programme risk register and has been rescored. The programme risk is no scoring the same as agency risk. While this is not an exact mirror the dependencies and assumption are similar enough to take on board the mitigations and actions planned. Programme risk owner notified of mirrored risk on SSS register. Risk Reworded To be owned by AM-previously owned by Mo Rooney | 27/04/20 External Relationships/Stakeholder- Finance- Reputation- Behaviours- Cultural- People- Operational Readiness While retaining this risk it needs to be re-phrased to reflect the horizon change. May make more sense to re-phrase as an opportunity (?) REPHRASE
AS-R048 (SS-R012) | 2019-01-30 | Resource |  | 4 | 3 | 12 | 4 | 3 | 12 | 0 |  | Limited |  |  | Static | 20 |  | MG | Miriam Craven |  | Updated 02/04/20 by AK(on behalf of Action Owner) Note from Action Owner: | 27/04/20 Workforce Planning- Reputational- Financial- Operational Readiness. Linked to AS-R001a, 002a and 034a
AS-R050 (SS-R044) | 2019-01-30 | Policy |  | 5 | 2 | 10 | 5 | 2 | 10 | 0 |  | Limited |  |  | Static | 15 |  | MG | Miriam Craven |  |  | 27/04/2020 Reputational- External Relationships/Stakeholders BUT is there scope to de-escalate based on current situation or is there now a risk that supercedes this? Or rephrase as an opportunity? REPHRASE
AS-R053 (SS-R025) | 2019-01-30 | Policy |  | 4 | 3 | 12 | 4 | 3 | 12 | 0 |  | Limited |  |  | Static | 15 |  | AR | Janet Richardson |  | 14/02/20- Proposed for closure at Risk Review Board (Feb) but now Deep Dive at next RRB (March). AR invited to attend for Agency perspective. | 27/04/20 Information Governance- Reputation De-escalate but high level Divisional Risk (Operations/CDO).
AS-R056 | 2019-01-31 | Governance |  | 3 | 4 | 12 | 3 | 4 | 12 | 0 |  | Insufficient |  |  | Static | 15 |  | AM | Miriam Craven |  | Release Management and Change board now meeting regularly to discuss TOR and purpose. | 27/04/20 Inclusive Comms- Operational Readiness- Culture De-escalate.
AS-R058a (Linked to CDO risk CDO-115) | 2019-01-31 | Operational Delivery |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Limited |  |  | Static | 20 |  | AR | Janet Richardson |  | 28/02/20- Update from CDO mirrored risk CDO-115 | 27/04/20 Operational Readiness- Culture- Reputation- External Relationships/Stakeholders
AS-R060 | 2019-03-06 | Compliance |  | 2 | 2 | 4 | 2 | 2 | 4 | 0 |  | Insufficient |  |  | Static | 10 |  | AM | Miriam Craven |  | Reworded 06/03/19 | 27/04/20 People- Culture- Behaviours Potentially de-escalate but discuss with action/risk owner.
AS-R061 | 2019-03-20 | Governance |  | 4 | 3 | 12 | 4 | 3 | 12 | 0 |  | Reasonable |  |  | Static | 15 | On-going | AM | Miriam Craven |  | 14/02/20- Proposed change of Action owner-to be discussed | 27/04/2020 External Relationships/Stakeholder- People- Reputational Linked with AS-R060 Requires follow up with Action Owner
AS-R062 (SS-R054) | 2019-03-26 | Governance |  | 4 | 4 | 16 | 4 | 2 | 8 | 8 |  | Limited |  |  | Static | 15 |  | CK | Miriam Craven |  | 28/02/20- Risk rephrased and accepted by Action Owner and Risk Owner. Accepted at Risk Review Group March 20 Linked to Programme Risk SS-R054 (current score 15) | 27/04/2020 Potential category change to Compliance Reputation- Finance- Information Governance- Information Security- Operational Readiness.
AS-R063 (SS-R022) | 2019-06-25 | Operational Delivery |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Insufficient |  |  | Static | 20 |  | JG | Janet Richardson |  | Linked to Programme risk SS-R022 Updated 13/09/19 by Risk Management Function: Follow up with Assessment Project leads once established in role. | 27/04/20 External Relationships/Stakeholders- Reputational- Finance- Operational Readiness Needs to be rephrased- not necessarily an Assessment Delivery Model risk, rather a Service Design risk- IF it is to capture an Assessment Model risk then new risk is required. REPHRASE
AS-R064 (CDO RR as SMT-010 & Programme as SS-R063) | 2019-09-18 | Operational Delivery |  | 4 | 4 | 16 | 4 | 3 | 12 | 4 |  | Reasonable |  |  | Decrease | 20 |  | AR/AM | Miriam Craven |  | Update 17/02/19- Risk presented to Audit and Assurance Committee February 2020 for Deep Dive Update 27/09/19 Update from CDO mirrored risk SMT-010 Update 19/09/19-this risk was added with approval from SLT on Monday 16th Sept 2019. This risk is mirrored across Programme and CDO registers | 27/04/20 External Relationships/Stakeholders- People- Finance- Reputation- Operational Readiness Linked to AS-R063 REPHRASE
AS-R065 (New Risk) | 2020-03-20 | Policy |  |  |  |  | 4 | 4 | 16 | [6 empty] | 15 |  | MF | James Wallace |  |  | 27/04/20 External Relationships/Stakeholders- Reputation- Finance- Culture- People- Behaviour Linked to AS-R015- do the risks say the same thing? Is one more strategic than the other or cumulative impact?
AS-R066 (New Risk) | 2020-03-20 | Policy |  |  |  |  | 4 | 5 | 20 | [6 empty] | 15 |  | MF | James Wallace |  |  | 27/04/20 Information Governance- Finance- Reputation- Information Security- Behaviours- Operational Readiness Linked to AS-R15a, 065
AS-R070 (New Risk) | 2020-03-20 | Operational Delivery |  | 5 | 5 | 25 | 5 | 4 | 20 | 5 |  | Limited |  | Treat |  | 20 |  | JC | Janet Richardson |  |  | 27/04/20 Reputation- Financial- People- Culture- Behaviours The risk needs to be rephrased- potential comparison with AS-R029. Both under review. REPHRASE
AS-R071 (New Risk) | 2020-03-20 | Operational Delivery |  |  |  | 0 | 5 | 5 | 25 | -25 | [5 empty] | 20 | [5 empty] | 27/04/20 Operational Readiness- External Relationships/Stakeholder- Reputation- Financial Discussion needed with Risk Owner Related AS-R063
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1
[6 empty] | 0 | 1 | 1 | 1 | -1 | [5 empty] | 1

## Risk Reference Guide
Risk Status |  |  |  | Risk Movement |  | Example Risk Definition
Proposed New Risk |  |  |  | Decreasing |  | The following risk examples are for overarching Social Security Scotland level risks. Your project may need to have a specific risk around the same subject. Need Agency examples
Closed - New |  |  |  | Increasing
Closed - Transfer to Project |  |  |  | New
Closed - Old |  |  |  | Static
New - Escalated from Project
Open
New
Proposed Closed Risk
Risk Response | Definition
Tolerate | An informed decision to accept the likelihood and impact of a particular risk. The risk should be monitored to ensure the risk response is still correct.
Creating a Risk Description
Treat | Proactive actions taken to reduce the probability of the event occurring through some form of control or reduce the impact of the event should it occur. |  |  |  |  | When recording a risk it should be captured using a specific form to allow it to be more easily assessed and analysed. Risk can be broken down into three parts: Cause – “if” statement Event – “then” statement Effect – “resulting in” statement
Transfer | Shifting the responsibility or burden for loss to another party. For example through insurance. Note: This should be used with caution – in reality it is often impossible to transfer a risk effectively. For example, if the risk to the Scottish Government is around reputation but a contractor is only obliged to compensate us financially, the risk cannot be considered well-managed.
Terminate | Involves changing some aspect of the Programme, Service or Product Area so that the risk either can no longer have an impact or can no longer happen.
Exploit | Seizing an opportunity to ensure that an opportunity will happen and the impact will be realised. |  |  |  |  | Risk Owner Definitions
[6 empty] | Risk Owner | • Overall responsibility for the management, monitoring and control of a specific risk captured on a Risk Register at either the Programme, Service or Product level including implementation of the selected risk response. • Approval of the escalation or closure of a risk. • Support the Risk Action Owner in any aspects of managing a risk.
Category | Definition
Communications | Risks that arise as a result of the Agency’s communications activity or which will have a significant impact on Agency communications – e.g. the risk that incorrect information is included in an Agency publication. |  |  |  |  | Risk Action Owner | • Ensuring allocated risks are appropriately captured on the appropriate risk register. • Develop and implement the risk response for allocated risks and maintenance of the relevant entries on the appropriate risk register. • Ensure risk updates are applied to the appropriate risk register or reported to the Programme Risk and Issue Manager where appropriate. • Ensure allocated risks are reported and escalated as per the process outlined in the Programme Risk Management Strategy. • Active communication with Risk Owner on all aspects of the management of allocated risks.
Compliance | Risk that arise as a result of requirements on the Agency to comply with its stratutory obligations- e.g. data protection legislation, employment law etc.
Financial | Risks associated with the management of, or which will have a significant impact on Agency non-finances – e.g. risk of fraud, risk over overspending etc.
Governance | Risks that arise as a result of activity (or inactivity) in the Agency’s governance space – e.g. risks around any potential failure to agree Agency Agreements with DWP
Operational Delivery | Risks that arise as a result of, or which will have a significant impact on the Agency’s operational activities. N.B. - for the purpose of this exercise, we recommend defining ‘operational’ quite narrowly, i.e. activities connected with the receipt of applications for, the determination of entitlement to, and the award of devolved benefits. ‘Operational’ does not mean, e.g. communications activity.
Policy | Risks that arise as a result of activity in the policy or political space – e.g. changes in policy which impact on the delivery of agency services
Programme | Risks that arise as a result of activity (or inactivity) in the Programme space or in relation to the Agency’s relationship with and dependencies on the Programme – e.g. risk that products delivered by the Programme may not be fit for purpose.
Resource | Risks associated with, or which will have a significant impact on Agency non-financial resources – e.g. risk that the Agency will not have sufficient staff in post, risks around suitability and availability of accommodation etc.
Security | Risks that arise as a result of requirements on the Agency to ensure that its people and other assets are kept safe and secure – e.g. risk of cyber-security attack.
Technology | Risks that arise as a result of changes to, or failures of technology which impact on the delivery of Agency services – e.g. system failure which means Agency staff are unable to verify customers’ IDs.
Descriptor | 1 – Rare | 2 – Low | 3 – Medium | 4 – High | 5 – Very high
Likelihood (e.g.) | 1% to 5% chance of occurring - extremely unlikely to occur | 6% to 25% chance of occurring - unlikely to occur | 26% to 50% chance of occurring - fairly likely to occur | 51% to 75% chance of occurring - more likely to occur than not | > 75% chance of occurring - almost certain to occur
Impact ranges from Negligible (1) to Very High (5).
Severity descriptors | 1 - Negligible | 2 - Low | 3 – Medium | 4 - High | 5 – Very High
| No real impact on achieving objectives, | Minor impact on objectives, requires little overall change in approach. Few resource consequences. | Moderate impact on objectives that may require multiple changes in approach, procedure or process. Acceptable level of resource consequences. | Significant and unacceptable impact on objectives that would require a material change to critical approach, procedure or process. Resource implications would be challenging to absorb within current operational circumstances. | Destructive and unacceptable impact on objectives that would result in a major change to overall approach. Potentially large resource consequences that outweigh current operational circumstances.

## Risk Scoring Guide
What is a risk?- a risk is an uncertain event that, should it occur, will impact on the achievement of our objectives
Descriptor | 1 – Rare | 2 – Low | 3 – Medium | 4 – High | 5 – Very high
Likelihood (e.g.) | 1% to 5% chance of occurring - extremely unlikely to occur | 6% to 25% chance of occurring - unlikely to occur | 26% to 50% chance of occurring - fairly likely to occur | 51% to 75% chance of occurring - more likely to occur than not | > 75% chance of occurring - almost certain to occur
Impact ranges from Negligible (1) to Very High (5).
Severity descriptors | 1 - Negligible | 2 - Low | 3 – Medium | 4 - High | 5 – Very High
| No real impact on achieving objectives, | Minor impact on objectives, requires little overall change in approach. Few resource consequences. | Moderate impact on objectives that may require multiple changes in approach, procedure or process. Acceptable level of resource consequences. | Significant and unacceptable impact on objectives that would require a material change to critical approach, procedure or process. Resource implications would be challenging to absorb within current operational circumstances. | Destructive and unacceptable impact on objectives that would result in a major change to overall approach. Potentially large resource consequences that outweigh current operational circumstances.
The combines scores on a 5 x 5 matrix will give scores ranging from 1 to 25; this gives equal weighting to both "Impact" and "Likelihood"
The bold line shows the "escalation score". When a risk score moves from 12 to 15 the risk needs to be escalated to Risk Owner, SLT and Audit and Assurance Committee.
Impact | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Likelihood
Total Risk Score Guide
Descriptor | 0 – 3 Low | 4 – 9 Medium | 10 – 19 High | Over 19 – Very high
Guide | Acceptable level of risk subject to regular passive monitoring. | Acceptable level of risk exposure subject to regular active monitoring | Unacceptable level of risk which requires controls to be put in place to reduce exposure. | Unacceptable level of risk exposure that requires immediate mitigating action.
Proximity
| <1 month | 1
| 2 - 6 months | 2
| over 6 months | 3

## Agency Issues Log (hidden)
ID | Date Identified | Status | Category | Severity Rating | Issue Description | Issue Owner | Issue Action Owner | Identified By | Cause and Impact Summaruy | Responses Actions (Current Progress & Planned) | Date Closed | Final Resolution Summary | Associated Risk ID or Dependency ID (if applicable) | Related Change Request ID (if applicable) | Updated By | Notes
AI-001 |  |  |  |  | Due to the transfer and delivery of devolved benefits from UK government to Social Security Scotland Agency, claimants may find the new arrangements difficult to understand given the high degree of overlap between reserved and devolved benefits, this may result in potential customer confusion creating and extra demand on Operations. | Operational Delivery | 2019-07-03 | Medium | Impact: *Clients are currently experience confusion regarding who is maintaining their benefits. Options: * On going communications across all available channels to clarify which benefits are owned by Scottish Governement | On Going |  | Open |  | 2019-07-03 | Simon Mitchell | This is currently logged as a risk on DWP Scottish Devolution Programme Risk Log-this is NOT a risk for the agency as this is currently being experienced and therefore captured on Issues Log
AI-002 |  |  |  |  | Due to the early withdrawal of the Development team for Best Start Foods, the Agency now must prepare to take on board business as usual activity that it is not resourced to do. | Governance | 2019-08-05 | Medium |  | On going |  | Open | Anne Mackie | 2019-08-05 | Simon Mitchell | This risk was rejected as a strategic risk at SLT 29th July 2019. The overall effect is as a result of the IT debt that will be handed over to the Agency when BSF goes to live running and the lack of resource to work on MVP and guidance development for improvement runs.

## Mirrored Risk (hidden)
CDO RISKS- Linked to AS-R005a
CDO-115 mirrored with AS-R058a
Programme Risk-Assumption on SSS
SS-R062 | New | 2019-08-05 | Delivery | Lisa Baron-Broadhurst | IF the Programme is unable to deliver the extensive and potentially complex evidence gathering capability promised for Disability Benefits (initially for DACYP, then DAOP and DAWAP), THEN we will not meet the ministerial commitment to reduce the burden on clients to gather evidence for claims, RESULTING IN a poor service to claimants and reputational damage for SG and Ministers. | 4 | 4 | 16 | 4 | 4 | 16 | 0 | Treat | 9 | John Paul Liddle | 2019-08-05 | Static | 2019-09-23

## Do Not Delete (hidden)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Communications
Compliance
Financial
Governance
Operational Delivery
Policy
Programme
Resource
Security
Technology
Sunbstantial
Reasonable
Limited
Insufficient
Increase
Decrease
Static
High
Medium
Low
Open
Closed
Treat
Tolerate
Transfer
Terminate
Exploit

## Removed from SRR
Risk ID | Date Added | Risk Type | Risk Description | Current Impact | Current Likelihood | Current Risk Score | Actions Planned | Tolerance Level | Imact Date | Action Owner | Risk Owner | Changes to Risk Explanation | NOTES
AS-R031 | 2019-01-23 | Technology |  | 4 | 2 | 8 |  |  | 15 | JC | Janet Richardson |  | 14/02/20- Risk Closure Accepted. Risk is being managed with in Transformation and Change Team JA
AS-R005a | 2019-01-23 | Technology |  | 5 | 5 | 25 |  |  | 15 | GW | Andy McClintock |  | 28/01/20- JA(Transformation and Change)- Accepts transfer to register- Risk Management Function to liaise with CDO and T&C to transfer.
AS-R038 | 2019-01-23 | Resource |  | 4 | 4 | 16 | 4 | 4 | 16 |  | Insufficient |  |  | Static | 20 |  | LY | James Wallace |  | 19/02/20- Risk now closed with agreement from Risk Review Group Feb 20
ASR019 | 2019-01-23 | Political |  |  |  | 0 |  | 1 |  |  |  |  | Merged with ASR 017-See 024 and 049 below
ASR024 | 2019-01-23 | Policy |  | 3 | 4 | 12 |  | 15 |  |  | James Wallace |  | Merged with ASR026-See 017 and 049 below
ASR026 | 2019-01-23 | Security |  |  |  | 0 |  | 1 |  |  |  |  | Merged with ASR 024
ASR010 | 2019-01-23 | Communications |  | 4 | 4 | 16 |  | 20 |  |  | Mo Rooney |  | Merged with ASR 027,028, 042 & 051
ASR027 | 2019-01-23 | Communications |  |  |  | 0 |  | 1 |  |  |  |  | Merged with ASR 010, 028, 042 & 051
ASR042 | 2019-01-23 | Communications |  |  |  | 0 |  | 1 |  |  |  |  | Merged with ASR010, 027, 028 & 051
ASR058 | 2019-01-31 | Operational Delivery |  | 4 | 5 | 20 |  | 1 |  |  |  | RISK IS STILL ON REGISTER BUT HAS BEEN RE-WORDED.
ASR028 | 2019-01-23 | Communications |  | 4 | 4 | 16 |  | 20 |  |  | Miriam Craven |  | Merged with ASR 010, 027, 042 & 051
ASR051 (SS-R032) | 2019-01-30 | Communications |  | 3 | 3 | 9 |  | 20 |  |  | Mo Rooney |  | Merged with ASR010, 027, 028 * 042
ASR014 | 2019-01-23 | Compliance |  | 4 | 4 | 16 |  | 10 |  |  | Mo Rooney |  | Merged with ASR016
ASR016 | 2019-01-23 | Compliance |  | 4 | 4 | 16 |  | 10 |  |  | Mo Rooney |  | Merged with ASR014
ASR060 | 2019-01-31 | Compliance |  | 2 | 2 | 4 |  | 10 |  |  | Mo Rooney |  | Reworded
ASR041 | 2019-01-23 | Compliance |  | 5 | 3 | 15 |  | 10 |  |  | Ally MacPhail
ASR059 | 2019-01-31 | Compliance |  | 4 | 4 | 16 |  | 10 |  |  | Mo Rooney |  | Learning risk.
ASR012 | 2019-01-23 | Financial |  | 4 | 4 | 16 |  | 15 |  |  | James Wallace |  | Merged with ASR 025& 052
ASR025 | 2019-01-23 | Financial |  | 3 | 4 | 12 |  | 15 |  |  | James Wallace |  | Merged with ASR 012& 052
ASR052 (SS-R026) | 2019-01-30 | Financial |  | 4 | 3 | 12 |  | 15 |  |  | James Wallace |  | Merged with ASR 012 & 025
ASR011 | 2019-01-23 | Governance |  | 4 | 4 | 16 |  | 15 |  |  | Mo Rooney |  | Merged with ASR018,020,036, now AS-R011a | NB-In discussion with MG, Action owner, about potentially rephrasing AS-R011a as two separate risks between Agency Agreements and Culture.
ASR018 | 2019-01-23 | Governance |  | 4 | 3 | 12 |  | 15 |  |  | Mo Rooney |  | Merged with ASR011, 020, 036 now AS-R011a | NB-In discussion with MG Action owner, about potentially rephrasing AS-R011a as two separate risks between Agency Agreements and Culture.
ASR020 | 2019-01-23 | Governance |  | 3 | 5 | 15 | ACTION PLAN TAKEN FROM SRR v.01 * SLWG established as part of the SG2020 Improvement Priority work - theme of Wellbeing and Diversity identified for focussed work. * Colleague Investment Hour sessions scheduled to cover equality & diversity , wellbeing, resilience and mindfulness, time and inbox management *Learning Offer developed by each Division in relation to survey results and local issues. Wellbeing events scheduled for December in conjunction with employee assistance programme. * Mental Health first aiders identified and trained. Working across SG to confirm how best to signpost to raise employee awareness of support. | 15 |  |  | Mo Rooney |  | Merged with ASR011, 018, 036 now AS-R011a | NB-In discussion with MG, Action owner, about potentially rephrasing AS-R011a as two separate risks between Agency Agreements and Culture.
ASR036 | 2019-01-23 | Governance |  | 4 | 3 | 12 |  | 15 |  |  | Mo Rooney |  | Merged with ASR011, 018, 020 Now AS-R011a | NB-In discussion with MG, Action owner, about potentially rephrasing AS-R011a as two separate risks between Agency Agreements and Culture.
ASR057 | 2019-01-31 | Governance |  | 4 | 3 | 12 |  | 15 |  | MG | Mo Rooney | Transferred to Unit Risk Log
ASR002 | 2019-01-23 | Operational Delivery |  | 4 | 4 | 16 |  | 20 |  |  | Mo Rooney |  | Merged with ASR006, 009, 022, 030
ASR006 | 2019-01-23 | Operational Delivery |  | 4 | 5 | 20 |  | 20 |  |  | Tracy Mcintyre |  | Merged with ASR002, 009, 022, 030
ASR009 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 |  | 20 |  |  | Tracy Mcintyre |  | Merged with ASR002, 006,022, 030
ASR022 | 2019-01-23 | Operational Delivery |  | 4 | 5 | 20 |  | 20 |  |  | Tracy Mcintyre |  | Merged with ASR002, 006, 009, 030
ASR030 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 |  | 20 |  |  | David Wallace |  | Merged with ASR002, 006, 009, 022 Also no represented in ASR047a
ASR047 (SSR031/022A) | 2019-01-30 | Operational Delivery |  | 5 | 4 | 20 |  | 20 |  |  | Mo Rooney | Reworded to better reflect the risk | To be owned by A
ASR015 | 2019-01-23 | Policy |  | 4 | 5 | 20 |  | 15 |  |  | James Wallace |  | Merged with ASR024
ASR024 | 2019-01-23 | Policy |  | 3 | 4 | 12 |  | 15 |  |  | James Wallace |  | Merged with ASR015
ASR017 | 2019-01-23 | Policy |  | 2 | 4 | 8 |  | 15 |  |  | Mo Rooney |  | Merged with ASR049
ASR049 (SS-014a/024a) | 2019-01-30 | Policy |  | 4 | 4 | 16 |  | 15 |  |  | Mo Rooney |  | Merged ASR017
ASR054 (no ref in SRRv.01) | 2019-01-30 | Policy |  | 5 | 4 | 20 |  | 15 |  |  | Tracy Mcintyre |  | Transgerred to Policy Risk Log
ASR001 | 2019-01-23 | Programme |  | 4 | 4 | 16 |  | 15 |  |  | Miriam Craven, James Wallace and Tracy McIntyre |  | Merged with ASR003 & 004 To be jointly owned with Miriam, James and Tracy Previous Action Owner-Mo Rooney
ASR003 | 2019-01-23 | Programme |  | 4 | 4 | 16 |  | 15 |  |  | Miriam Craven, James Wallace and Tracy McIntyre |  | Merged with ASR001 & 004 To be jointly owned with Miriam, James and Tracy Previous Action Owner-Mo Rooney
ASR004 | 2019-01-23 | Programme |  | 5 | 4 | 20 |  | 15 |  |  | Miriam Craven, James Wallace and Tracy McIntyre |  | Merged with ASR 001 & 003 To jointly owned with Miriam, James and Tracy Previous Action Owner: Mo Rooney See QR Doc for suggested rewording and new potential Risk. "Operations" replaced with "Agency"
ASR034 | 2019-01-23 | Resource |  | 5 | 5 | 25 |  | 20 |  |  | AM |  | Merged with ASR035
ASR035 | 2019-01-23 | Resource |  | 4 | 5 | 20 |  | 20 |  |  | AM |  | Merged with ASR034
ASR037 | 2019-01-23 | Resource |  | 5 | 4 | 20 |  | 20 |  |  | AM |  | Merged with ASR039
ASR039 | 2019-01-23 | Resource |  | 5 | 4 | 20 |  | 20 |  |  | AM |  | Merged with ASR037
ASR040 | 2019-01-23 | Resource |  | 3 | 2 | 6 |  | 20 |  |  | AM | Risk reworded
ASR032 | 2019-01-23 | Resource |  | 4 | 4 | 16 |  | 20 |  |  | AM | Risk reworded
ASR033 | 2019-01-23 | Resource |  | 4 | 5 | 20 |  | 20 |  |  | AM | Removed as part of ASR001a
ASR023 | 2019-01-23 | Security |  | 4 | 5 | 20 |  | 15 |  | MF | James Wallace | Transferred to Unit Risk Log
ASR005 | 2019-01-23 | Technology |  | 5 | 5 | 25 |  | 15 |  |  | AM | Risk reworded | Moved from Mo responsibility to A
ASR008 | 2019-01-23 | Financial |  | 5 | 5 | 25 |  | 15 |  | SG | James Wallace |  | Original Wording
ASR021 | 2019-01-23 | Financial |  | 4 | 4 | 16 |  | 15 |  | SG | James Wallace |  | Original Wording
ASR015a | 2019-01-23 | Policy |  | 4 | 4 | 16 |  | 15 |  | MF | James Wallace | Discussion with Action Owner resulting in a reduction of likelihood from "5" to "4" (March 2019). | Original Wording
ASR012a | 2019-03-06 | Financial |  | 4 | 4 | 16 |  | 15 |  | SG | James Wallace |  | Merged Risks ASR012, 025 & 052 Original Wording
ASR034a | 2019-01-23 | Resource |  | 5 | 5 | 25 |  | 20 |  | JS | AM |  | Merged Risks ASR034 & ASR035 Reworded byAM 10/05/19
AS-R002a | 2019-01-23 | Operational Delivery |  | 4 | 4 | 16 |  |  | 20 |  | JS | Mo Rooney |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE. Update provided by JS 18/07/19-JSrecommends reduction in Likelihood score from 4 > 3. Recommendation sent to SLT w/c 29th July.
AS-R005a | 2019-01-23 | Technology |  | 5 | 5 | 25 | 5 | 5 | 25 | [6 empty] | 0 | 15 |  | GW | AM |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE. Update 22/07/19: Risk score unchanged. SLT feel Operations have yet to feel the benefit of any current mitigations and actions. 18/06/19- Linked to CDO risks SS-R058 and SS-R059 17/06/19 CDO have accpeted ownership of this risk and awaiting details of Action Owner; AMwill remain as Risk Owner currently until such time as CDO member joins Agency SLT. All mitigation response lies with CDO 20/05/19- Meeting CDO on 5th June to discuss current action plans. Moved from Mo responsibility to AM. Relates to SS-R057 (SPM risk Programme RR)
AS-R048 (SS-R012) | 2019-01-30 | Resource |  | 4 | 3 | 12 |  |  | 20 |  | MG | Mo Rooney |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***. 17/06/19 Risk score amended. The original score of "16" was transferred in error; the score now reflects the residual score on Programme Risk register and therefore. Being retained by Programme Possible mitigations in ASR008 (CDO-066) with CAD providing revised resourcing figures.
AS-R062 | 2019-03-26 | Governance |  | 4 | 4 | 16 | 4 | 4 | 16 | [6 empty] | 0 | 15 |  | JH | Mo Rooney |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***. New Risk added 26/03/19
| AS-R034a | 2019-01-23 | Resource |  | 5 | 5 | 25 |  |  | 20 | JS | AM |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***. Merged Risks ASR034 & ASR035 Reworded by AM updated from CM 10/05/19. The Agency needs to be clear and set out its estate requirements in order for the right building to be procured?
AS-R029 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 |  |  | 20 |  | KC | Tracy Mcintyre |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R058a | 2019-01-31 | Operational Delivery |  | 4 | 4 | 16 |  |  | 20 | AR | Tracy Mcintyre |  | 16/08/19- Update from CDO on mirrored risk CDO-115. 20/05/19- Meeting CDO on 5th June to discuss current action plans. From CDO Risk Log 17/05/19- Link to CDO risk CDO-115 Risk reworded Relates to SS-R057 (SPM Programme RR) See CDO update at ASR005a | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R014a | 2019-03-06 | Compliance |  | 4 | 4 | 16 |  |  | 10 | NM/CK | Mo Rooney |  | 30/08/19-Update provided by CK (joint action owner) 13/08/19- Action Owners updated to include CKat Risk Owner's request 03/07/19- Update from NM Merged Risks ASR014 & ASR016 Updated from CDO Risk log (CDO-065) 23/04/19 Partial Agency mitigation. No change to score | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R037a | 2019-01-23 | Resource |  | 5 | 4 | 20 |  |  | 20 | NB | Ally MacPhail |  | Merged Risks ASR037 & ASR039 | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R008 | 2019-01-23 | Financial |  | 5 | 5 | 25 | 5 | 5 | 25 |  | Limited |  |  |  | Static | 15 |  | SG | James Wallace |  | 30/08/19- Risk Description to be updated pending discussion with Action and Risk Owner reworded by Risk Owner 25/03/19 Linked to CDO Risk CDO-66 Partial Agency mitigation. No change to score | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R014a | 2019-03-06 | Compliance |  | 4 | 4 | 16 |  |  | 10 | NM/CK | Mo Rooney |  | 30/08/19-Update provided by CK (joint action owner) 13/08/19- Action Owners updated to include CK at Risk Owner's request 03/07/19- Update from NM. Merged Risks ASR014 & ASR016 Updated from CDO Risk log (CDO-065) 23/04/19 Partial Agency mitigation. No change to score | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R002a | 2019-01-23 | Operational Delivery |  | 4 | 4 | 16 |  |  | 20 | JS | Mo Rooney |  | Update provided by JS16/08/19- JS recommends reduction in Likelihood score from 4 > 3. Recommendation sent to SLT w/c 29th July but score change not accepted-more information required. | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
ASR040a | 2019-03-06 | Resource |  | 3 | 2 | 6 (no change to score) |  |  | 20 |  | SA | AM |  | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R029 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 | 5 | 5 | 25 |  | Limited |  |  |  | Static | 20 |  | JC/KC | Tracy McIntyre |  | Updated 13/08/19 by Action Owner | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.
AS-R029 | 2019-01-23 | Operational Delivery |  | 5 | 5 | 25 |  |  | 20 | JC/KC | Janet Richardson |  | Updated 21/10/19- Reworded at request of Chief Executive Updated 13/08/19 by Action Owner | [8 empty] | ***RISK STILL LIVE BUT OLD VERSIONS CAPTURED HERE***.

## Removed from SRR March 2020
Risk ID | Risk Removed | Risk Type | Risk Description | Untreated Impact | Untreated Likelihood | Inherent Risk Score | Current Impact | Current Likelihood | Residual Risk Score | Change in Risk Score due to Action | Key Mitigating Controls-Current and Proposed | Control Confidence Level | Actions | Risk Response | Risk Score Movement | Tolerance Level | Impact Date | Action Owner | Risk Owner | Changes to Risk Explanation | NOTES
AS-R008 | 2020-03-27 | Financial |  | 5 | 5 | 25 | 5 | 2 | 10 | 15 |  | Limited |  |  | Static | 15 |  | SG | James Wallace |  | 03/03/20- Risk to be removed- Risk is mirrored on Finance risk register as FIN-02 and FIN-13, both of which are being suitably managed at the divisional level. 24/09/19- SLT have accepted a request to reduce the Likelihood score from 5 to 2 based on current mitigating controls and actions planned 18/09/19- Request to adjust risk score issued to SLT to accept based on current activity taking place (Change to Likelihood only: reducting from 5 to 3) 30/08/19- Risk Description to be updated pending discussion with Action and Risk Owner reworded by Risk Owner 25/03/19 Linked to CDO Risk CDO-66 Partial Agency mitigation. No change to score
AS-R021 | 2020-03-27 | Financial |  | 4 | 4 | 16 | 4 | 4 | 16 | 0 |  | Insufficient |  |  | Static | 15 |  | SG | James Wallace |  | Update 31/10/19- Risk linked to proposed new risk on Programme Risk Register (SS-R068). Presented to RRB 07/11/19 Reworded by Risk Owner 25/03/19